## Sheet2
[8 empty] | Project Code | Scope Completion. | Time Completion. | Project Code | Sum of Scope Completion
[8 empty] | 51410 | 0.44 | 0.60577 | 51397 | 19.75
[8 empty] | Grand Total | 0.44 | 0.60577 | 51410 | 7.04
[11 empty] | 51407 | 0.6
51382
51368
51268
51419
51280
51396
51345
51422
51415
51391
51411
51414
51413
51166
51095
51370
51373
Category | Upcoming |  |  | Category | Late | [5 empty] | 51398
51307
Project Code | Task | Finish Date. | Start Date. | Project Code | Task | Start Date. | Finish Date. |  |  |  | 51325
51410 | LT& TT Installation | 2025-10-14 | 2025-09-29 | 51410 | [6 empty] | 51366
| Team-1: Tank Instruments-Mechanical Fabrication Works | 2025-10-14 | 2025-09-29 |  | Customs Clearance | 2025-07-18 | 2025-07-18 |  |  |  | 51164
| Construction | 2025-12-26 | 2025-09-29 |  | Supply of Installation Materials(Cables,Junction box,computer equipment) | 2025-06-07 | 2025-07-25 |  |  |  | 51260
| Customs Clearance | 2025-09-19 | 2025-09-19 |  | Shipment to Addis | 2025-06-30 | 2025-07-17 |  |  |  | 51143
| Delivery to Site | 2025-09-26 | 2025-09-22 |  | Delivery to Site | 2025-07-21 | 2025-07-25 |  |  |  | 51395
| Factory Acceptance Test & Training | 2025-08-29 | 2025-08-25 | [7 empty] | 51412
| Opening Manhole | 2025-09-29 | 2025-09-29 | [7 empty] | 51212
| Shipment to Addis | 2025-09-18 | 2025-09-01 | [7 empty] | 51336
51408
51339
51406
[11 empty] | Grand Total | 27.39

## Projects
Project Code | Item | Description | Owner | Start Date | Finish Date | Percentage Complete | Category | Predecessor | Status | Column1
51397 | Completion of Nairobi Site |  |  | 2025-08-14 | 2025-08-14 | 100% | Upcoming
51397 | ELDORET |  |  | 2025-08-19 | 2025-09-01 | 0% | Upcoming
51397 | Mobilization |  |  | 2025-08-19 | 2025-08-19 | 0% | Upcoming
51397 | Site establishment |  |  | 2025-08-19 | 2025-08-19 | 0% | Upcoming
51397 | Personnel mobilization |  |  | 2025-08-19 | 2025-08-19 | 0% | Upcoming
51397 | Soft Soil excavation |  |  | 2025-08-20 | 2025-08-21 | 0% | Upcoming
51397 | Civil Works |  |  | 2025-08-20 | 2025-08-28 | 0% | Upcoming
51397 | Manhole construction |  |  | 2025-08-22 | 2025-08-26 | 0% | Upcoming
51397 | MOMBASA |  |  | 2025-06-03 | 2025-07-22 | 18% | Late
51397 | Installation works |  |  | 2025-07-15 | 2025-07-18 | 0% | Late
51397 | Cabling works |  |  | 2025-06-03 | 2025-06-05 | 0% | Late
51397 | Commisioning |  |  | 2025-07-21 | 2025-07-22 | 0% | Late
51397 | On-job training |  |  | 2025-07-22 | 2025-07-22 | 0% | Late
51397 | Cleaning & hand-over of site |  |  | 2025-07-22 | 2025-07-22 | 0% | Late
51397 | Completion of Mombasa site |  |  | 2025-07-22 | 2025-07-22 | 0% | Late
51397 | Installation of sounder/siren |  |  | 2025-07-18 | 2025-07-18 | 0% | Late
51397 | Installation of panel |  |  | 2025-07-17 | 2025-07-17 | 0% | Late
51397 | Installation of detection equipment |  |  | 2025-07-15 | 2025-07-16 | 0% | Late
51397 | Termination of cables |  |  | 2025-06-05 | 2025-06-05 | 0% | Late
51397 | Laying of cables |  |  | 2025-06-03 | 2025-06-04 | 0% | Late
51397 | Simulation of alarms |  |  | 2025-07-21 | 2025-07-21 | 0% | Late
51397 | Construction |  |  |  |  | 77% | Workstream
51397 | Procurement |  |  |  |  | 100% | Workstream
51397 | Commisioning | [5 empty] | Workstream
51397 | Preliminaries |  |  |  |  | 100% | Workstream
51407 | Basemement 03 |  |  | 2025-08-11 | 2025-12-25 | 2% | Upcoming
51407 | Strucrural Works |  |  | 2025-08-11 | 2025-11-13 | 6% | Upcoming
51407 | Horizontal Members (Column Base/Retaining Wall Base) |  |  | 2025-08-11 | 2025-09-10 | 15% | Upcoming
51407 | BRC Mesh/DPM |  |  | 2025-08-11 | 2025-08-14 | 0% | Upcoming
51407 | Blinding |  |  | 2025-08-11 | 2025-08-15 | 100% | Upcoming
51407 | Surface Drain, Formwork and Sump |  |  | 2025-08-12 | 2025-08-18 | 0% | Upcoming
51407 | Marking for Vertical Members - Column Base |  |  | 2025-08-12 | 2025-08-12 | 0% | Upcoming
51407 | Shuttering |  |  | 2025-08-19 | 2025-09-01 | 0% | Upcoming
51407 | Project Particulars & Contract |  |  | 2025-03-14 | 2025-05-19 | 33% | Late
51407 | Mobilisation & General |  |  | 2025-03-14 | 2025-05-19 | 33% | Late
51407 | Provision for Temporary Water |  |  | 2025-04-02 | 2025-05-12 | 0% | Late
51407 | Provision for Temporary Electricity |  |  | 2025-04-02 | 2025-05-12 | 0% | Late
51407 | Hoarding |  |  | 2025-04-02 | 2025-05-19 | 60% | Late
51407 | Mobilisation |  |  | 2025-04-09 | 2025-05-19 | 5% | Late
51407 | Ramp Construction |  |  | 2025-04-10 | 2025-05-13 | 0% | Late
51407 | Completion of preconstruction works |  |  | 2025-05-13 | 2025-05-13 | 0% | Late
51407 | Construction |  |  |  |  | 0% | Workstream
51407 | Preliminaries |  |  |  |  | 0% | Workstream
51407 | Commisioning |  |  |  |  | 0% | Workstream
51407 | Procurement |  |  |  |  | 0% | Workstream
51413 | Disconnection & re-cabling of the density meters |  |  | 2025-08-12 | 2025-08-18 | 0% | Upcoming
51413 | Termination of the cables |  |  | 2025-08-13 | 2025-08-22 | 50% | Upcoming
51413 | COMMISSIONING |  |  | 2025-08-20 | 2025-09-08 | 0% | Upcoming
51413 | System configuration |  |  | 2025-08-20 | 2025-08-26 | 0% | Upcoming
51413 | Fine tuning for the tanks |  |  | 2025-08-27 | 2025-09-08 | 0% | Upcoming
51413 | TRAINING |  |  | 2025-09-11 | 2025-09-15 | 0% | Upcoming
51413 | On-job training |  |  | 2025-09-11 | 2025-09-15 | 0% | Upcoming
51413 | HAND-OVER |  |  | 2025-09-15 | 2025-09-16 | 0% | Upcoming
51413 | PROCUREMENT |  |  | 2025-04-03 | 2025-08-04 | 96% | Late
51413 | Cabling works |  |  | 2025-07-02 | 2025-08-08 | 61% | Late
51413 | Laying of cables |  |  | 2025-07-02 | 2025-07-11 | 70% | Late
51413 | Foreign procurement |  |  | 2025-04-03 | 2025-08-04 | 96% | Late
51413 | Delivery to site |  |  | 2025-07-31 | 2025-08-04 | 0% | Late
51413 | Decommisioning of old cables |  |  | 2025-07-15 | 2025-07-17 | 0% | Late
51413 | Preliminaries |  |  |  |  | 100% | Workstream
51413 | Commisioning |  |  |  |  | 0% | Workstream
51413 | Construction |  |  |  |  | 0% | Workstream
51413 | Procurement |  |  |  |  | 96% | Workstream
51410 | Factory Acceptance Test & Training |  |  | 2025-08-25 | 2025-08-29 | 0% | Upcoming
51410 | Shipment to Addis |  |  | 2025-09-01 | 2025-09-18 | 0% | Upcoming
51410 | Customs Clearance |  |  | 2025-09-19 | 2025-09-19 | 0% | Upcoming
51410 | Delivery to Site |  |  | 2025-09-22 | 2025-09-26 | 0% | Upcoming
51410 | CONSTRUCTION |  |  | 2025-09-29 | 2025-12-26 | 0% | Upcoming
51410 | Team-1: Tank Instruments-Mechanical Fabrication Works |  |  | 2025-09-29 | 2025-10-14 | 0% | Upcoming
51410 | LT& TT Installation |  |  | 2025-09-29 | 2025-10-14 | 0% | Upcoming
51410 | Opening Manhole |  |  | 2025-09-29 | 2025-09-29 | 0% | Upcoming
51410 | Supply of Installation Materials(Cables,Junction box,computer equipment) |  |  | 2025-06-07 | 2025-07-25 | 43% | Late
51410 | Shipment to Addis |  |  | 2025-06-30 | 2025-07-17 | 0% | Late
51410 | Customs Clearance |  |  | 2025-07-18 | 2025-07-18 | 0% | Late
51410 | Delivery to Site |  |  | 2025-07-21 | 2025-07-25 | 0% | Late
51410 | Construction |  |  |  |  | 0% | Workstream
51410 | Commisioning |  |  |  |  | 0% | Workstream
51410 | Preliminaries |  |  |  |  | 100% | Workstream
51410 | Procurement |  |  |  |  | 69% | Workstream

## Sheet3
[7 empty] | Priority | Count of Priority | Division | Count of Division | Performance Category | Count of Performance Category | Project Code | Budget Status Category | Count of Budget Status Category
[9 empty] | Civil | 3 | Critical Delay | 16 | 51095 | Critically Over Budget | 22
[9 empty] | Electrical | 12 | On Track | 12 | 51143 | Over Budget | 1
[9 empty] | Instrumentation | 14 | Slightly Behind | 21 | 51164 | Under Budget | 1
[9 empty] | Mechanical | 5 | Grand Total | 49 | 51166 | Within Budget | 10
[9 empty] | Grand Total | 34 |  |  | 51212 | Grand Total | 34
51260
51268
51280
51307
51325
51336
51339
51345
51366
51368
51370
51373
51382
51391
51395
51396
51397
51398
Project Name | Project Code | Scope Completion. | Time Completion. | Budget Spent. | Performance index. | Issues/Risks. | [6 empty] | 51406
| 51397 | 79% | 109.8% | 84.83% | 0.8 | [7 empty] | 51407
| 51410 | 44% | 60.58% | 131.1% | 0.9 | [7 empty] | 51408
| 51407 | 3% | 25.2% | #DIV/0! | 0.1 | [7 empty] | 51410
| 51382 |  | 149.3% | 97.23% | [8 empty] | 51411
| 51368 |  | 301.6% | 117.5% | [8 empty] | 51412
| 51268 |  | -1.883% | #DIV/0! | [8 empty] | 51413
| 51419 |  | 88.65% | 1294% | [8 empty] | 51414
| 51280 |  | -1.788% | 10384% | [8 empty] | 51415
| 51396 |  | 315.4% | #DIV/0! | [8 empty] | 51419
| 51345 |  | -1.307% | #DIV/0! | [8 empty] | 51422
| 51422 |  | 162.2% | 33151% | [8 empty] | Grand Total
| 51415 |  | 114% | 119.6%
| 51391 |  | 359.5% | 95.47%
| 51411 |  | 344.8% | 149.4%
| 51414 |  | 129.6% | #DIV/0!
| 51413 |  | 97.84% | 111.3%
| 51166 |  | 133.2% | 103.1%
| 51095 |  | 393.4% | 123.8%
| 51370 |  | 1263% | 100%
| 51373 |  | 325.5% | 147.2%
| 51398 |  | 233% | #DIV/0!
| 51307 |  | -1.72% | 104.7%
| 51325 |  | -1.504% | 59.56%
| 51366 |  | 336.1% | 219.2%
| 51164 |  | 0% | 111.6%
| 51260 |  | 0% | #DIV/0!
| 51143 |  | 120.7% | 337%
| 51395 |  | 122% | #DIV/0!
| 51412 |  | 1000% | 100%
| 51212 |  | 295.6% | -95.17%
| 51336 |  | 174.7% | 94.49%
| 51408 |  | 179.2% | 104.5%
| 51339 |  | 685.7% | 92.93%
| 51406 |  | 215.1% | 105.4%

## Portfolio
Project Code | Description | Task | Start Date | Finish Date | Percentage Complete | Category | Scope Completion | Time Completion | Performance index | Performance Category | Priority | Issues/Risks | Division | Budget amount | Total Amount Spent | Budget Spent | Budget Status | Budget Status Category | Location | Amount received | CO Amount | ProjectedGross Margin (%) | Actual GrossMargin (%) | % Deviation of the Profit Margin
51422 | Supply of Pressure Gauges and Pressure Transmitters |  | 2025-04-17 | 2025-06-30 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 1644805.4105 | 4961.5385 |  |  |  | [(-1.2921, 36.8219), (-0.0917, 34.7680), (-0.3031, 36.0800)] |  | 2088639
51419 | Supply, Installation and Commissioning of Overfill Protection System |  | 2025-04-12 | 2025-08-31 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 1308312.4556 | 101075 |  |  |  | [(-0.3031, 36.0800), (0.5143, 35.2698), (0.0167, 37.0728)] |  | 4922287.4741
51415 | Special Stringing Works At Timau Sand Pro Farm Between Tower T97-T99 (Completion Of Nanyuki - Isiolo 132kv Transmission Line) |  | 2025-04-15 | 2025-07-31 | [5 empty] | #DIV/0! |  | 5 | Electrical | 3355000 | 2805000 |  |  |  | [(0.5143, 35.2698), (-1.2921, 36.8219), (-3.3753, 36.8551)] |  | 30201464
51414 | Supply of ASCO Pilot Repair Kit |  | 2025-04-10 | 2025-07-17 | [5 empty] | #DIV/0! |  | 5 | Mechanical | 271617.97 | 0 |  |  |  | [(-3.3753, 36.8551), (-2.5164, 32.9016), (-3.3869, 36.6829)] |  | 713232
51413 | Supply and Installation of ATG for Lower Tank Farm |  | 2025-04-01 | 2025-08-18 | 0.73 |  | 73% | 98.56% |  | Critical Delay |  | 5 | Instrumentation | 15961819.5498 | 14343197.35 |  |  | Critically Over Budget | [(-6.7924, 39.2083), (-3.3869, 36.6829), (-2.5164, 32.9016)] |  | 40205880
51412 | Valve Service For Total Changamwe |  | 2025-03-28 | 2025-04-11 | [5 empty] | #DIV/0! |  | 5 | Mechanical | 17049.16 | 17049.16 |  |  |  | [(-3.3869, 36.6829), (-6.7924, 39.2083), (-8.5560, 34.9910)] |  | 57093
51411 | Supply of Fisher spares |  | 2025-01-27 | 2025-03-26 | [5 empty] | #DIV/0! |  | 5 | Mechanical | 328804.372 | 220075.8 |  |  |  | [(-8.5560, 34.9910), (-3.3869, 36.6829), (-6.7924, 39.2083)] |  | 747291.9021
51410 | Design, Supply and Installation of Radar Based Hybrid Tank Farm Management System (TFMS) / ATG |  | 2025-03-12 | 2025-09-30 | 0.44 |  | 44% | 77.72% |  | Critical Delay |  | 5 | Instrumentation | 38226214.7538 | 29147711 |  |  | Critically Over Budget | [(9.0108, 38.7613), (7.6735, 36.8351), (11.5681, 37.3614)] |  | 91059810
51408 | Supply of Rosemount Pressure Transmitters on PS10 RTG System |  | 2025-02-24 | 2025-05-31 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 1659827.52 | 1588893.15 |  |  |  | [(7.6735, 36.8351), (11.5681, 37.3614), (5.9667, 38.7167)] |  | 9322927.8621
51407 | Proposed TG Riruta Apartments In Riruta |  | 2025-02-01 | 2026-06-30 | 0.03 |  | 3% | 38.13% |  | Critical Delay |  | 5 | Civil | #REF! | #REF! |  |  | Within Budget | [(11.5681, 37.3614), (9.0108, 38.7613), (5.9667, 38.7167)] |  | #REF!
51406 | Radar Level Gauge 3900s and Troubleshooting of three tanks at PS 10 |  | 2025-01-27 | 2025-04-30 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 5840781.25 | 5543902.7692 |  |  |  | [(5.9667, 38.7167), (7.6735, 36.8351), (9.0108, 38.7613)] |  | 24931186.8
51398 | Supply and Installation of Electrical and Mechanical Solar System |  | 2024-12-18 | 2025-03-31 | [5 empty] | #DIV/0! |  | 5 | Electrical | 1702885.2 | 0 |  |  |  | [(9.0108, 38.7613), (11.5681, 37.3614), (12.0360, 39.0433)] |  | 2469183.54
51397 | Supply , Installation and Commissioning of Intristically safe Gas Leak Detector, Flame Detector and Training at Nairobi, Eldoret and Mombasa LPG Terminals. |  | 2024-12-12 | 2025-03-12 | 0.86 |  | 86% | 274.4% |  | Critical Delay |  | 5 | Instrumentation | 6634370.83 | 7821059.5776 |  |  | Critically Over Budget | [(12.0360, 39.0433), (11.5681, 37.3614), (7.6735, 36.8351)] |  | 21659935.75
51396 | Construction of New Burhani Engineers Ltd Office |  | 2024-11-01 | 2025-01-31 | [5 empty] | #DIV/0! |  | 5 | Electrical | #REF! | #REF! |  |  |  | [(7.6735, 36.8351), (9.0108, 38.7613), (12.0360, 39.0433)] |  | #REF!
51395 | KWAL SLA 2024-2025 |  | 2024-12-03 | 2025-06-30 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 112000 | 0 |  |  |  | [(12.0360, 39.0433), (5.9667, 38.7167), (9.0108, 38.7613)] |  | 872000
51391 | Kimugu Powerhouse VCB Synchronizing Switchboard Replacement |  | 2024-10-17 | 2025-01-09 | [5 empty] | #DIV/0! |  | 5 | Electrical | 4874356.1366 | 5105476 |  |  |  | [(5.9667, 38.7167), (7.6735, 36.8351), (11.5681, 37.3614)] |  | 8782522
51382 | Supply, Installation and Commissioning of Receipt Mass flow Meters from Ship |  | 2024-09-25 | 2025-04-30 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 84899826.7588 | 87316966.3286 |  |  |  | [(11.5681, 37.3614), (9.0108, 38.7613), (12.0360, 39.0433)] |  | 170029246.12
51373 | 67500-KSL Boiler-PRV details for Servicing |  | 2024-02-25 | 2024-08-08 | [5 empty] | #DIV/0! |  | 5 | Mechanical | 89249.16 | 60612.6364 |  |  |  | [(-6.7924, 39.2083), (-3.3869, 36.6829), (-8.5560, 34.9910)] |  | 126599.441
51370 | Repair and Electrical Works |  | 2024-08-01 | 2024-08-31 | [5 empty] | #DIV/0! |  | 5 | Electrical | 916329.5 | 916329.5 |  |  |  | [(-8.5560, 34.9910), (-2.5164, 32.9016), (-3.3869, 36.6829)] |  | 1011528.8
51368 | Annual Testing of Sarasin RSBD Thermal Relief Valves |  | 2024-07-25 | 2024-11-30 | [5 empty] | #DIV/0! |  | 5 | Mechanical | 191166.4 | 162632.32 |  |  |  | [(-2.5164, 32.9016), (-6.7924, 39.2083), (-8.5560, 34.9910)] |  | 898442.99
51366 | Tank Gauging Works at Nairobi LPG |  | 2024-07-01 | 2024-10-31 | [5 empty] | #DIV/0! |  | 5 | Instrumentation | 741000 | 338100 |  |  |  | [(-1.2921, 36.8219), (-0.0917, 34.7680), (0.5143, 35.2698)] |  | 3231460
51345 | Renovation Works and Maintenance In Mombasa |  | 2024-01-01 | [6 empty] | #DIV/0! |  | 5 | Electrical | #REF! | 8631035.96 |  |  |  | [(0.0167, 37.0728), (-0.3031, 36.0800), (-1.2921, 36.8219)] |  | 9500400
51339 | Fire Fighting System Upgrade at OLA Energy Ltd Mombasa Terminal |  | 2023-11-30 | 2024-02-29 | [5 empty] | #DIV/0! |  | 5 | Electrical | 3821812 | 4112477.0707 |  |  |  | [(-0.3031, 36.0800), (-0.0917, 34.7680), (0.0167, 37.0728)] |  | 7882559.03
51336 | Supply and Installation of 2X1MW Medium Speed Diesel Engines for Wajir Power Station. |  | 2023-10-16 | 2024-11-02 | [5 empty] | #DIV/0! |  | 5 | Electrical | 140980192.1713 | 149198399.4662 |  |  |  | [(-0.0917, 34.7680), (0.5143, 35.2698), (-1.2921, 36.8219)] |  | 249106016.98
51325 | Supply, Install and Commission of Computer Based Solar System With Computer Work - Stations, Software Tracking System with Large Scale Solar PV Plant That Feeds To The National Grid |  | 2023-10-05 | [6 empty] | #DIV/0! |  | 5 | Electrical | 44681155.15 | 75019436.2572 |  |  |  | [(0.0167, 37.0728), (-0.3031, 36.0800), (0.5143, 35.2698)] |  | 40617628.0517
51307 |  |  | 2023-07-01 | [6 empty] | #DIV/0! |  | 5 | Civil | 13734076.2716 | 13121160.2 |  |  |  | [(9.0108, 38.7613), (7.6735, 36.8351), (5.9667, 38.7167)] |  | 19060984.2716
51280 |  |  | 2023-06-01 | [6 empty] | #DIV/0! |  | 5 | Instrumentation | 254400 | 2450 |  |  |  | [(11.5681, 37.3614), (12.0360, 39.0433), (9.0108, 38.7613)] |  | 1671416
51268 |  |  | 2023-04-20 | [6 empty] | #DIV/0! |  | 5 | Instrumentation | #REF! | #REF! |  |  |  | [(12.0360, 39.0433), (5.9667, 38.7167), (11.5681, 37.3614)] |  | #REF!
51260 | [9 empty] | #DIV/0! |  | 5 | Instrumentation | 41400 | 0 |  |  |  | [(7.6735, 36.8351), (12.0360, 39.0433), (9.0108, 38.7613)] |  | 480000
51212 |  |  | 2022-09-01 | 2023-09-01 | [5 empty] | #DIV/0! |  | 5 | Civil | 151579374.4 | 159265468.81 |  |  |  | [(5.9667, 38.7167), (11.5681, 37.3614), (12.0360, 39.0433)] |  | 172124506.49
51166 |  |  | 2024-04-16 | 2025-04-16 | [5 empty] | #DIV/0! |  | 5 | Electrical | 262006557.64 | 254060633.9683 | [5 empty] | 371712426.1638
51164 | [9 empty] | #DIV/0! |  | 5 | Instrumentation | 3519978.91 | 3153560.69 | [5 empty] | 11091386.8
51143 |  |  | 2022-01-01 | 2024-12-31 | [5 empty] | #DIV/0! |  | 5 | Electrical | 182000 | 54000 | [5 empty] | 531668
51095 |  |  | 2021-09-09 | 2022-09-09 | [5 empty] | #DIV/0! |  | 5 | Electrical | 193170669.37 | 155979250.2728 | [5 empty] | 288237075.28