## Sheet2
[8 empty] | Project Code | Scope Completion. | Time Completion. | Project Code | Sum of Scope Completion
[8 empty] | 51410 | 0.44 | 0.60577 | 51397 | 19.75
[8 empty] | Grand Total | 0.44 | 0.60577 | 51410 | 7.04
[11 empty] | 51407 | 0.6
51382
51368
51268
51419
51280
51396
51345
51422
51415
51391
51411
51414
51413
51166
51095
51370
51373
Category | Upcoming |  |  | Category | Late | [5 empty] | 51398
51307
Project Code | Task | Finish Date. | Start Date. | Project Code | Task | Start Date. | Finish Date. |  |  |  | 51325
51410 | LT& TT Installation | 2025-10-14 | 2025-09-29 | 51410 | [6 empty] | 51366
| Team-1: Tank Instruments-Mechanical Fabrication Works | 2025-10-14 | 2025-09-29 |  | Customs Clearance | 2025-07-18 | 2025-07-18 |  |  |  | 51164
| Construction | 2025-12-26 | 2025-09-29 |  | Supply of Installation Materials(Cables,Junction box,computer equipment) | 2025-06-07 | 2025-07-25 |  |  |  | 51260
| Customs Clearance | 2025-09-19 | 2025-09-19 |  | Shipment to Addis | 2025-06-30 | 2025-07-17 |  |  |  | 51143
| Delivery to Site | 2025-09-26 | 2025-09-22 |  | Delivery to Site | 2025-07-21 | 2025-07-25 |  |  |  | 51395
| Factory Acceptance Test & Training | 2025-08-29 | 2025-08-25 | [7 empty] | 51412
| Opening Manhole | 2025-09-29 | 2025-09-29 | [7 empty] | 51212
| Shipment to Addis | 2025-09-18 | 2025-09-01 | [7 empty] | 51336
51408
51339
51406
[11 empty] | Grand Total | 27.39

## Projects
Project Code | Item | Description | Owner | Start Date | Finish Date | Percentage Complete | Category | Predecessor | Status | Column1
51397 | Completion of Nairobi Site |  |  | 4588300% | 2025-08-14 | 100% | Upcoming
51397 | ELDORET |  |  | 4588800% | 2025-09-01 | 0% | Upcoming
51397 | Mobilization |  |  | 4588800% | 2025-08-19 | 0% | Upcoming
51397 | Site establishment |  |  | 4588800% | 2025-08-19 | 0% | Upcoming
51397 | Personnel mobilization |  |  | 4588800% | 2025-08-19 | 0% | Upcoming
51397 | Soft Soil excavation |  |  | 4588900% | 2025-08-21 | 0% | Upcoming
51397 | Civil Works |  |  | 4588900% | 2025-08-28 | 0% | Upcoming
51397 | Manhole construction |  |  | 4589100% | 2025-08-26 | 0% | Upcoming
51397 | MOMBASA |  |  | 4581100% | 2025-07-22 | 18% | Late
51397 | Installation works |  |  | 4585300% | 2025-07-18 | 0% | Late
51397 | Cabling works |  |  | 4581100% | 2025-06-05 | 0% | Late
51397 | Commisioning |  |  | 4585900% | 2025-07-22 | 0% | Late
51397 | On-job training |  |  | 4586000% | 2025-07-22 | 0% | Late
51397 | Cleaning & hand-over of site |  |  | 4586000% | 2025-07-22 | 0% | Late
51397 | Completion of Mombasa site |  |  | 4586000% | 2025-07-22 | 0% | Late
51397 | Installation of sounder/siren |  |  | 4585600% | 2025-07-18 | 0% | Late
51397 | Installation of panel |  |  | 4585500% | 2025-07-17 | 0% | Late
51397 | Installation of detection equipment |  |  | 4585300% | 2025-07-16 | 0% | Late
51397 | Termination of cables |  |  | 4581300% | 2025-06-05 | 0% | Late
51397 | Laying of cables |  |  | 4581100% | 2025-06-04 | 0% | Late
51397 | Simulation of alarms |  |  | 4585900% | 2025-07-21 | 0% | Late
51397 | Construction |  |  |  |  | 77% | Workstream
51397 | Procurement |  |  |  |  | 100% | Workstream
51397 | Commisioning | [5 empty] | Workstream
51397 | Preliminaries |  |  |  |  | 100% | Workstream
51407 | Basemement 03 |  |  | 4588000% | 2025-12-25 | 2% | Upcoming
51407 | Strucrural Works |  |  | 4588000% | 2025-11-13 | 6% | Upcoming
51407 | Horizontal Members (Column Base/Retaining Wall Base) |  |  | 4588000% | 2025-09-10 | 15% | Upcoming
51407 | BRC Mesh/DPM |  |  | 4588000% | 2025-08-14 | 0% | Upcoming
51407 | Blinding |  |  | 4588000% | 2025-08-15 | 100% | Upcoming
51407 | Surface Drain, Formwork and Sump |  |  | 4588100% | 2025-08-18 | 0% | Upcoming
51407 | Marking for Vertical Members - Column Base |  |  | 4588100% | 2025-08-12 | 0% | Upcoming
51407 | Shuttering |  |  | 4588800% | 2025-09-01 | 0% | Upcoming
51407 | Project Particulars & Contract |  |  | 4573000% | 2025-05-19 | 33% | Late
51407 | Mobilisation & General |  |  | 4573000% | 2025-05-19 | 33% | Late
51407 | Provision for Temporary Water |  |  | 4574900% | 2025-05-12 | 0% | Late
51407 | Provision for Temporary Electricity |  |  | 4574900% | 2025-05-12 | 0% | Late
51407 | Hoarding |  |  | 4574900% | 2025-05-19 | 60% | Late
51407 | Mobilisation |  |  | 4575600% | 2025-05-19 | 5% | Late
51407 | Ramp Construction |  |  | 4575700% | 2025-05-13 | 0% | Late
51407 | Completion of preconstruction works |  |  | 4579000% | 2025-05-13 | 0% | Late
51407 | Construction |  |  |  |  | 0% | Workstream
51407 | Preliminaries |  |  |  |  | 0% | Workstream
51407 | Commisioning |  |  |  |  | 0% | Workstream
51407 | Procurement |  |  |  |  | 0% | Workstream
51413 | Disconnection & re-cabling of the density meters |  |  | 4588100% | 2025-08-18 | 0% | Upcoming
51413 | Termination of the cables |  |  | 4588200% | 2025-08-22 | 50% | Upcoming
51413 | COMMISSIONING |  |  | 4588900% | 2025-09-08 | 0% | Upcoming
51413 | System configuration |  |  | 4588900% | 2025-08-26 | 0% | Upcoming
51413 | Fine tuning for the tanks |  |  | 4589600% | 2025-09-08 | 0% | Upcoming
51413 | TRAINING |  |  | 4591100% | 2025-09-15 | 0% | Upcoming
51413 | On-job training |  |  | 4591100% | 2025-09-15 | 0% | Upcoming
51413 | HAND-OVER |  |  | 4591500% | 2025-09-16 | 0% | Upcoming
51413 | PROCUREMENT |  |  | 4575000% | 2025-08-04 | 96% | Late
51413 | Cabling works |  |  | 4584000% | 2025-08-08 | 61% | Late
51413 | Laying of cables |  |  | 4584000% | 2025-07-11 | 70% | Late
51413 | Foreign procurement |  |  | 4575000% | 2025-08-04 | 96% | Late
51413 | Delivery to site |  |  | 4586900% | 2025-08-04 | 0% | Late
51413 | Decommisioning of old cables |  |  | 4585300% | 2025-07-17 | 0% | Late
51413 | Preliminaries |  |  |  |  | 100% | Workstream
51413 | Commisioning |  |  |  |  | 0% | Workstream
51413 | Construction |  |  |  |  | 0% | Workstream
51413 | Procurement |  |  |  |  | 96% | Workstream
51410 | Factory Acceptance Test & Training |  |  | 4589400% | 2025-08-29 | 0% | Upcoming
51410 | Shipment to Addis |  |  | 4590100% | 2025-09-18 | 0% | Upcoming
51410 | Customs Clearance |  |  | 4591900% | 2025-09-19 | 0% | Upcoming
51410 | Delivery to Site |  |  | 4592200% | 2025-09-26 | 0% | Upcoming
51410 | CONSTRUCTION |  |  | 4592900% | 2025-12-26 | 0% | Upcoming
51410 | Team-1: Tank Instruments-Mechanical Fabrication Works |  |  | 4592900% | 2025-10-14 | 0% | Upcoming
51410 | LT& TT Installation |  |  | 4592900% | 2025-10-14 | 0% | Upcoming
51410 | Opening Manhole |  |  | 4592900% | 2025-09-29 | 0% | Upcoming
51410 | Supply of Installation Materials(Cables,Junction box,computer equipment) |  |  | 4581500% | 2025-07-25 | 43% | Late
51410 | Shipment to Addis |  |  | 4583800% | 2025-07-17 | 0% | Late
51410 | Customs Clearance |  |  | 4585600% | 2025-07-18 | 0% | Late
51410 | Delivery to Site |  |  | 4585900% | 2025-07-25 | 0% | Late
51410 | Construction |  |  |  |  | 0% | Workstream
51410 | Commisioning |  |  |  |  | 0% | Workstream
51410 | Preliminaries |  |  |  |  | 100% | Workstream
51410 | Procurement |  |  |  |  | 69% | Workstream

## Sheet3
| 34 | 982747032.3399 | 659559977.2055 | -49% |  |  | Priority | Count of Priority | Division | Count of Division |  | Performance Category | Count of Performance Category | Project Code | Budget Status Category | Count of Budget Status Category
[9 empty] | Civil | 3 |  | Critical Delay | 16 | 51095 | Critically Over Budget | 22
[9 empty] | Electrical | 12 |  | On Track | 12 | 51143 | Over Budget | 1
[9 empty] | Instrumentation | 14 |  | Slightly Behind | 21 | 51164 | Under Budget | 1
[9 empty] | Mechanical | 5 |  | Grand Total | 49 | 51166 | Within Budget | 10
[9 empty] | Grand Total | 34 |  |  |  | 51212 | Grand Total | 34
51260
51268
51280
51307
51325
51336
51339
51345
51366
51368
51370
51373
51382
51391
51395
51396
51397
51398
Project Name | Project Code | Scope Completion. | Time Completion. | Budget Spent. | Performance index. | Issues/Risks. | [7 empty] | 51406
Supply , Installation and Commissioning of Intristically safe Gas Leak Detector, Flame Detector and Training at Nairobi, Eldoret and Mombasa LPG Terminals. | 51397 | 79% | 109.8% | 84.83% | 0.8 | [5 empty] | -1.0983 |  |  | 51407
Design, Supply and Installation of Radar Based Hybrid Tank Farm Management System (TFMS) / ATG | 51410 | 44% | 60.58% | 131.1% | 0.9 | [5 empty] | -0.60577 |  |  | 51408
Proposed TG Riruta Apartments In Riruta | 51407 | 3% | 25.2% | #DIV/0! | 0.1 | [5 empty] | -0.25201 |  |  | 51410
Supply, Installation and Commissioning of Receipt Mass flow Meters from Ship | 51382 |  | 149.3% | 97.23% | [6 empty] | -1.4931 |  |  | 51411
Annual Testing of Sarasin RSBD Thermal Relief Valves | 51368 |  | 301.6% | 117.5% | [6 empty] | -3.0156 |  |  | 51412
| 51268 |  | -1.883% | #DIV/0! | [6 empty] | 0.018829 |  |  | 51413
Supply, Installation and Commissioning of Overfill Protection System | 51419 |  | 88.65% | 1294% | [6 empty] | -0.88652 |  |  | 51414
| 51280 |  | -1.788% | 10384% | [6 empty] | 0.01788 |  |  | 51415
Construction of New Burhani Engineers Ltd Office | 51396 |  | 315.4% | #DIV/0! | [6 empty] | -3.1538 |  |  | 51419
Renovation Works and Maintenance In Mombasa | 51345 |  | -1.307% | #DIV/0! | [6 empty] | 0.013071 |  |  | 51422
Supply of Pressure Gauges and Pressure Transmitters | 51422 |  | 162.2% | 33151% | [6 empty] | -1.6216 |  |  | Grand Total
Special Stringing Works At Timau Sand Pro Farm Between Tower T97-T99 (Completion Of Nanyuki - Isiolo 132kv Transmission Line) | 51415 |  | 114% | 119.6% | [6 empty] | -1.1402
Kimugu Powerhouse VCB Synchronizing Switchboard Replacement | 51391 |  | 359.5% | 95.47% | [6 empty] | -3.5952
Supply of Fisher spares | 51411 |  | 344.8% | 149.4% | [6 empty] | -3.4483
Supply of ASCO Pilot Repair Kit | 51414 |  | 129.6% | #DIV/0! | [6 empty] | -1.2959
Supply and Installation of ATG for Lower Tank Farm | 51413 |  | 97.84% | 111.3% | [6 empty] | -0.97842
| 51166 |  | 133.2% | 103.1% | [6 empty] | -1.3315
| 51095 |  | 393.4% | 123.8% | [6 empty] | -3.9342
Repair and Electrical Works | 51370 |  | 1263% | 100% | [6 empty] | -12.6333
67500-KSL Boiler-PRV details for Servicing | 51373 |  | 325.5% | 147.2% | [6 empty] | -3.2545
Supply and Installation of Electrical and Mechanical Solar System | 51398 |  | 233% | #DIV/0! | [6 empty] | -2.3301
| 51307 |  | -1.72% | 104.7% | [6 empty] | 0.017203
Supply, Install and Commission of Computer Based Solar System With Computer Work - Stations, Software Tracking System with Large Scale Solar PV Plant That Feeds To The National Grid | 51325 |  | -1.504% | 59.56% | [6 empty] | 0.015043
Tank Gauging Works at Nairobi LPG | 51366 |  | 336.1% | 219.2% | [6 empty] | -3.3607
| 51164 |  | 0% | 111.6% | [6 empty] | 0
| 51260 |  | 0% | #DIV/0! | [6 empty] | 0
| 51143 |  | 120.7% | 337% | [6 empty] | -1.2073
KWAL SLA 2024-2025 | 51395 |  | 122% | #DIV/0! | [6 empty] | -1.2201
Valve Service For Total Changamwe | 51412 |  | 1000% | 100% | [6 empty] | -10
| 51212 |  | 295.6% | -95.17% | [6 empty] | -2.9562
Supply and Installation of 2X1MW Medium Speed Diesel Engines for Wajir Power Station. | 51336 |  | 174.7% | 94.49% | [6 empty] | -1.7467
Supply of Rosemount Pressure Transmitters on PS10 RTG System | 51408 |  | 179.2% | 104.5% | [6 empty] | -1.7917
Fire Fighting System Upgrade at OLA Energy Ltd Mombasa Terminal | 51339 |  | 685.7% | 92.93% | [6 empty] | -6.8571
Radar Level Gauge 3900s and Troubleshooting of three tanks at PS 10 | 51406 |  | 215.1% | 105.4% | [6 empty] | -2.1505
0
[5 empty] | #DIV/0! | [5 empty] | 0
0
0
0
0
0
0
0
Live Projects
Total Budget
Total Spend
Budget Variance
LIVE PROJECTS DASHBOARD

## Portfolio
Project Code | Description | Task | Start Date | Finish Date | Percentage Complete | Category | Scope Completion | Time Completion | Performance index | Performance Category | Priority | Issues/Risks | Division | Budget amount | Total Amount Spent | Budget Spent | Budget Status | Budget Status Category | Location | Amount received | CO Amount | ProjectedGross Margin (%) | Actual GrossMargin (%) | % Deviation of the Profit Margin
51422 | Supply of Pressure Gauges and Pressure Transmitters |  | 2025-04-17 | 2025-06-30 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 1644805.4105 | 4961.5385 | 331.5112 |  |  | [(-1.2921, 36.8219), (-0.0917, 34.7680), (-0.3031, 36.0800)] |  | 2088639 | 0.2125 | 0.99984 | 0.78734
51419 | Supply, Installation and Commissioning of Overfill Protection System |  | 2025-04-12 | 2025-08-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 1308312.4556 | 101075 | 12.944 |  |  | [(-0.3031, 36.0800), (0.5143, 35.2698), (0.0167, 37.0728)] |  | 4922287.4741 | 0.73421 | 1 | 0.26579
51415 | Special Stringing Works At Timau Sand Pro Farm Between Tower T97-T99 (Completion Of Nanyuki - Isiolo 132kv Transmission Line) |  | 2025-04-15 | 2025-07-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 3355000 | 2805000 | 1.1961 |  |  | [(0.5143, 35.2698), (-1.2921, 36.8219), (-3.3753, 36.8551)] |  | 30201464 | 0.88891 | 1 | 0.11109
51414 | Supply of ASCO Pilot Repair Kit |  | 2025-04-10 | 2025-07-17 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Mechanical | 271617.97 | 0 |  |  |  | [(-3.3753, 36.8551), (-2.5164, 32.9016), (-3.3869, 36.6829)] |  | 713232 | 0.61917 | #VALUE! | #VALUE!
51413 | Supply and Installation of ATG for Lower Tank Farm |  | 2025-04-01 | 2025-08-18 | 0.73 |  | 73% | 98.56% | 74.07% | Critical Delay |  | 5 | Instrumentation | 15961819.5498 | 14343197.35 | 1.1128 |  | Critically Over Budget | [(-6.7924, 39.2083), (-3.3869, 36.6829), (-2.5164, 32.9016)] |  | 40205880 | 0.603 | 1 | 0.397
51412 | Valve Service For Total Changamwe |  | 2025-03-28 | 2025-04-11 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Mechanical | 17049.16 | 17049.16 | 1 |  |  | [(-3.3869, 36.6829), (-6.7924, 39.2083), (-8.5560, 34.9910)] |  | 57093 | 0.70138 | 0.99998 | 0.2986
51411 | Supply of Fisher spares |  | 2025-01-27 | 2025-03-26 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Mechanical | 328804.372 | 220075.8 | 1.4941 |  |  | [(-8.5560, 34.9910), (-3.3869, 36.6829), (-6.7924, 39.2083)] |  | 747291.9021 | 0.56001 | 1 | 0.43999
51410 | Design, Supply and Installation of Radar Based Hybrid Tank Farm Management System (TFMS) / ATG |  | 2025-03-12 | 2025-09-30 | 0.44 |  | 44% | 77.72% | 56.61% | Critical Delay |  | 5 | Instrumentation | 38226214.7538 | 29147711 | 1.3115 |  | Critically Over Budget | [(9.0108, 38.7613), (7.6735, 36.8351), (11.5681, 37.3614)] |  | 91059810 | 0.58021 | 1 | 0.41979
51408 | Supply of Rosemount Pressure Transmitters on PS10 RTG System |  | 2025-02-24 | 2025-05-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 1659827.52 | 1588893.15 | 1.0446 |  |  | [(7.6735, 36.8351), (11.5681, 37.3614), (5.9667, 38.7167)] |  | 9322927.8621 | 0.82196 | 1 | 0.17804
51407 | Proposed TG Riruta Apartments In Riruta |  | 2025-02-01 | 2026-06-30 | 0.03 |  | 3% | 38.13% | 7.867% | Critical Delay |  | 5 | Civil | #REF! | #REF! |  |  | Within Budget | [(11.5681, 37.3614), (9.0108, 38.7613), (5.9667, 38.7167)] |  | #REF! | #REF! | #REF! | #REF!
51406 | Radar Level Gauge 3900s and Troubleshooting of three tanks at PS 10 |  | 2025-01-27 | 2025-04-30 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 5840781.25 | 5543902.7692 | 1.0536 |  |  | [(5.9667, 38.7167), (7.6735, 36.8351), (9.0108, 38.7613)] |  | 24931186.8 | 0.76572 | 1 | 0.23428
51398 | Supply and Installation of Electrical and Mechanical Solar System |  | 2024-12-18 | 2025-03-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 1702885.2 | 0 |  |  |  | [(9.0108, 38.7613), (11.5681, 37.3614), (12.0360, 39.0433)] |  | 2469183.54 | 0.31034 | #VALUE! | #VALUE!
51397 | Supply , Installation and Commissioning of Intristically safe Gas Leak Detector, Flame Detector and Training at Nairobi, Eldoret and Mombasa LPG Terminals. |  | 2024-12-12 | 2025-03-12 | 0.86 |  | 86% | 274.4% | 31.34% | Critical Delay |  | 5 | Instrumentation | 6634370.83 | 7821059.5776 | 0.84827 |  | Critically Over Budget | [(12.0360, 39.0433), (11.5681, 37.3614), (7.6735, 36.8351)] |  | 21659935.75 | 0.6937 | 1 | 0.3063
51396 | Construction of New Burhani Engineers Ltd Office |  | 2024-11-01 | 2025-01-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | #REF! | #REF! |  |  |  | [(7.6735, 36.8351), (9.0108, 38.7613), (12.0360, 39.0433)] |  | #REF! | #REF! | #REF! | #REF!
51395 | KWAL SLA 2024-2025 |  | 2024-12-03 | 2025-06-30 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 112000 | 0 |  |  |  | [(12.0360, 39.0433), (5.9667, 38.7167), (9.0108, 38.7613)] |  | 872000 | 0.87156 | #VALUE! | #VALUE!
51391 | Kimugu Powerhouse VCB Synchronizing Switchboard Replacement |  | 2024-10-17 | 2025-01-09 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 4874356.1366 | 5105476 | 0.95473 |  |  | [(5.9667, 38.7167), (7.6735, 36.8351), (11.5681, 37.3614)] |  | 8782522 | 0.44499 | 1 | 0.55501
51382 | Supply, Installation and Commissioning of Receipt Mass flow Meters from Ship |  | 2024-09-25 | 2025-04-30 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 84899826.7588 | 87316966.3286 | 0.97232 |  |  | [(11.5681, 37.3614), (9.0108, 38.7613), (12.0360, 39.0433)] |  | 170029246.12 | 0.50068 | 1 | 0.49932
51373 | 67500-KSL Boiler-PRV details for Servicing |  | 2024-02-25 | 2024-08-08 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Mechanical | 89249.16 | 60612.6364 | 1.4725 |  |  | [(-6.7924, 39.2083), (-3.3869, 36.6829), (-8.5560, 34.9910)] |  | 126599.441 | 0.29503 | 0.99999 | 0.70496
51370 | Repair and Electrical Works |  | 2024-08-01 | 2024-08-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 916329.5 | 916329.5 | 1 |  |  | [(-8.5560, 34.9910), (-2.5164, 32.9016), (-3.3869, 36.6829)] |  | 1011528.8 | 0.094114 | 1 | 0.90588
51368 | Annual Testing of Sarasin RSBD Thermal Relief Valves |  | 2024-07-25 | 2024-11-30 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Mechanical | 191166.4 | 162632.32 | 1.1755 |  |  | [(-2.5164, 32.9016), (-6.7924, 39.2083), (-8.5560, 34.9910)] |  | 898442.99 | 0.78722 | 1 | 0.21277
51366 | Tank Gauging Works at Nairobi LPG |  | 2024-07-01 | 2024-10-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 741000 | 338100 | 2.1917 |  |  | [(-1.2921, 36.8219), (-0.0917, 34.7680), (0.5143, 35.2698)] |  | 3231460 | 0.77069 | 1 | 0.22931
51345 | Renovation Works and Maintenance In Mombasa |  | 2024-01-01 | [5 empty] | #DIV/0! | #DIV/0! |  | 5 | Electrical | #REF! | 8631035.96 |  |  |  | [(0.0167, 37.0728), (-0.3031, 36.0800), (-1.2921, 36.8219)] |  | 9500400 | #REF! | #VALUE! | #VALUE!
51339 | Fire Fighting System Upgrade at OLA Energy Ltd Mombasa Terminal |  | 2023-11-30 | 2024-02-29 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 3821812 | 4112477.0707 | 0.92932 |  |  | [(-0.3031, 36.0800), (-0.0917, 34.7680), (0.0167, 37.0728)] |  | 7882559.03 | 0.51516 | 1 | 0.48484
51336 | Supply and Installation of 2X1MW Medium Speed Diesel Engines for Wajir Power Station. |  | 2023-10-16 | 2024-11-02 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 140980192.1713 | 149198399.4662 | 0.94492 |  |  | [(-0.0917, 34.7680), (0.5143, 35.2698), (-1.2921, 36.8219)] |  | 249106016.98 | 0.43406 | 1 | 0.56594
51325 | Supply, Install and Commission of Computer Based Solar System With Computer Work - Stations, Software Tracking System with Large Scale Solar PV Plant That Feeds To The National Grid |  | 2023-10-05 | [5 empty] | #DIV/0! | #DIV/0! |  | 5 | Electrical | 44681155.15 | 75019436.2572 | 0.59559 |  |  | [(0.0167, 37.0728), (-0.3031, 36.0800), (0.5143, 35.2698)] |  | 40617628.0517 | -0.10004 | 1 | 1.1
51307 |  |  | 2023-07-01 | [5 empty] | #DIV/0! | #DIV/0! |  | 5 | Civil | 13734076.2716 | 13121160.2 | 1.0467 |  |  | [(9.0108, 38.7613), (7.6735, 36.8351), (5.9667, 38.7167)] |  | 19060984.2716 | 0.27947 | 1 | 0.72053
51280 |  |  | 2023-06-01 | [5 empty] | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 254400 | 2450 | 103.8367 |  |  | [(11.5681, 37.3614), (12.0360, 39.0433), (9.0108, 38.7613)] |  | 1671416 | 0.84779 | 0.99994 | 0.15214
51268 |  |  | 2023-04-20 | [5 empty] | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | #REF! | #REF! |  |  |  | [(12.0360, 39.0433), (5.9667, 38.7167), (11.5681, 37.3614)] |  | #REF! | #REF! | #REF! | #REF!
51260 | [8 empty] | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 41400 | 0 |  |  |  | [(7.6735, 36.8351), (12.0360, 39.0433), (9.0108, 38.7613)] |  | 480000 | 0.91375 | #VALUE! | #VALUE!
51212 |  |  | 2022-09-01 | 2023-09-01 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Civil | 151579374.4 | -159265468.81 | -0.95174 |  |  | [(5.9667, 38.7167), (11.5681, 37.3614), (12.0360, 39.0433)] |  | 172124506.49 | 0.11936 | 1 | 0.88064
51166 |  |  | 2024-04-16 | 2025-04-16 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 262006557.64 | 254060633.9683 | 1.0313 |  |  |  |  | 371712426.1638 | 0.29514 | 1 | 0.70486
51164 | [8 empty] | #DIV/0! | #DIV/0! |  | 5 | Instrumentation | 3519978.91 | 3153560.69 | 1.1162 |  |  |  |  | 11091386.8 | 0.68264 | 1 | 0.31736
51143 |  |  | 2022-01-01 | 2024-12-31 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 182000 | 54000 | 3.3704 |  |  |  |  | 531668 | 0.65768 | 0.99999 | 0.34231
51095 |  |  | 2021-09-09 | 2022-09-09 |  |  |  |  | #DIV/0! | #DIV/0! |  | 5 | Electrical | 193170669.37 | 155979250.2728 | 1.2384 |  |  |  |  | 288237075.28 | 0.32982 | 1 | 0.67018